## META
Key | Value
project_name | LNG Terminal
project_value | $1,050M
data_date | 2025-08-31
report_period | August 2025
contract_mc | 2027-03-31
forecast_mc | 2027-05-04
mc_variance_days | 34
spi | 0.93
cpi | 0.94
budget | 1050
forecast_cost | 1117
cost_variance | -67
contingency_remaining | 42
forecast_slip_days | 34
if_no_action_days | 12
cost_exposure_per_day | 420000
forecast_bias_days | 5
time_to_breach_days | 22
plan_reliability_ppc | 0.68
top_decision_text | Piping productivity 35% below plan
top_action_text | Add 2nd crew + marine logistics review
top_action_owner | Construction Mgr
top_action_deadline | 2025-10-14
top_action_no_action_impact_days | 28
top_action_no_action_impact_cost | 37.4
kpi_slip_trend | 12,16,20,24,28,34
kpi_no_action_trend | 2,4,6,7,9,12
kpi_cost_trend | 240,280,310,350,390,420
kpi_bias_trend | 1.4,2.1,3.0,3.8,4.5,5.2
kpi_breach_trend | 35,28,22,18,14,11

## Contradictions
conflict | system_a | system_b | severity
P6 says 72% ¦ field count shows 54% | P6 | Field | High
P6 shows 280 crew ¦ only 215 on site | P6 | Field | High
ROS passed for cable trays ¦ P6 not updated | P6 | Procurement | Med

## Cost_Performance
period | area | discipline | budget | earned_value | actual_cost | plan_pct | actual_pct | earned_pct
Mar | All | Construction |  |  |  | 4.2 | 3.8 | 3.5
Apr | All | Construction |  |  |  | 5.8 | 5 | 4.8
May | All | Construction |  |  |  | 7 | 6.1 | 5.9
Jun | All | Construction |  |  |  | 8.4 | 7 | 6.8
Jul | All | Construction |  |  |  | 9.1 | 7.6 | 7.5
Aug | All | Construction |  |  |  | 10 | 8.2 | 7.9
Sep | All | Construction |  |  |  | 11 | 8.6 | 8.2
Mar | All | Engineering |  |  |  | 6 | 5.8 | 5.6
Apr | All | Engineering |  |  |  | 7.2 | 7 | 6.8
May | All | Engineering |  |  |  | 8.1 | 7.9 | 7.7
Jun | All | Engineering |  |  |  | 8.8 | 8.5 | 8.3
Jul | All | Engineering |  |  |  | 9.2 | 8.9 | 8.7
Aug | All | Engineering |  |  |  | 9.5 | 9.2 | 9
Sep | All | Engineering |  |  |  | 9.7 | 9.4 | 9.2
Mar | All | Procurement |  |  |  | 5 | 4.6 | 4.3
Apr | All | Procurement |  |  |  | 6.5 | 5.9 | 5.5
May | All | Procurement |  |  |  | 7.4 | 6.8 | 6.4
Jun | All | Procurement |  |  |  | 8 | 7.3 | 6.9
Jul | All | Procurement |  |  |  | 8.4 | 7.6 | 7.2
Aug | All | Procurement |  |  |  | 8.7 | 7.9 | 7.5
Sep | All | Procurement |  |  |  | 8.9 | 8.1 | 7.7
Apr | All | All | 110
May | All | All | 98
Jun | All | All | 78
Jul | All | All | 58
Aug | All | All | 42
Apr | All | Forecast_Error | [5 empty] | 1
May | All | Forecast_Error | [5 empty] | 2
Jun | All | Forecast_Error | [5 empty] | 5
Jul | All | Forecast_Error | [5 empty] | 4
Aug | All | Forecast_Error | [5 empty] | 6
Aug | Pacific Marine | All |  | 48 | 59
Aug | Modular Systems | All |  | 35 | 38
Aug | Coastal Concrete | All |  | 28 | 30
Aug | NorthSteel | All |  | 18 | 19

## Actions_Log
action | owner | impact_days | critical_path | cost_exposure_m
Add 2nd piping crew, float at 0d | Construction | -8 | Yes | 12.4
Expedite valves, ROS missed by 14d | Procurement | -3 | Yes | 5.6
Resequence hydrotest, pred, lag 6d | Planning | -4 | Yes | 3.2
Add crew (closure) | Construction | -5 | Yes
Release IFC (closure) | Engineering | -5 | No
Expedite valves (closure) | Procurement | 0 | Yes

## Float_Erosion
period | view | item | float_days
BL | Area | A2-Process | 18
May | Area | A2-Process | 20
Jun | Area | A2-Process | 19
Jul | Area | A2-Process | 14
Aug | Area | A2-Process | 10
BL | Area | A4-Utilities | 25
May | Area | A4-Utilities | 22
Jun | Area | A4-Utilities | 20
Jul | Area | A4-Utilities | 15
Aug | Area | A4-Utilities | 8
BL | Area | A1-Tank Farm | 21
May | Area | A1-Tank Farm | 19
Jun | Area | A1-Tank Farm | 16
Jul | Area | A1-Tank Farm | 12
Aug | Area | A1-Tank Farm | 5
BL | Discipline | Piping | 20
May | Discipline | Piping | 16
Jun | Discipline | Piping | 11
Jul | Discipline | Piping | 5
Aug | Discipline | Piping | -3
BL | Discipline | E&I | 22
May | Discipline | E&I | 20
Jun | Discipline | E&I | 18
Jul | Discipline | E&I | 14
Aug | Discipline | E&I | 8
BL | Discipline | Mechanical | 18
May | Discipline | Mechanical | 17
Jun | Discipline | Mechanical | 15
Jul | Discipline | Mechanical | 12
Aug | Discipline | Mechanical | 6
BL | Discipline | Structural | 25
May | Discipline | Structural | 23
Jun | Discipline | Structural | 21
Jul | Discipline | Structural | 19
Aug | Discipline | Structural | 15
Previous | Worsening | A3-Marine | -2
Previous | Worsening | A1-Tank Farm | -1
Current | Worsening | A3-Marine | -6
Current | Worsening | A1-Tank Farm | -5

## Production_Validation
discipline | required_rate | actual_rate | gap_pct | historical_max
Civil | 100 | 92 | -8 | 105
Steel | 85 | 78 | -8 | 90
Piping | 120 | 78 | -35 | 92
E&I | 70 | 64 | -9 | 72

## Productivity_Factor
period | discipline | pf_value
Apr | Piping | 1.08
May | Piping | 1.14
Jun | Piping | 1.22
Jul | Piping | 1.31
Aug | Piping | 1.42
Apr | E&I | 1.02
May | E&I | 1.05
Jun | E&I | 1.07
Jul | E&I | 1.1
Aug | E&I | 1.12
Apr | Steel | 0.98
May | Steel | 1.01
Jun | Steel | 1.03
Jul | Steel | 1.05
Aug | Steel | 1.06
Apr | Civil | 0.95
May | Civil | 0.96
Jun | Civil | 0.97
Jul | Civil | 0.98
Aug | Civil | 0.99

## Recovery_Plans
recovery_lever | gain_days | feasibility | constraint
2nd piping crew | 8 | Medium | Labour availability
Weekend shifts | 4 | High | Union agreement
Resequence hydrotest | 3 | Low | Predecessor logic
Expedite valve delivery | 3 | Medium | Vendor lead time
Fast-track prefab modules | 3 | Medium | Fabrication yard capacity

## Subcontractors
contractor | earned_value_m | actual_cost_m | delay_impact_days | cpi | spi
Pacific Marine | 48 | 59 | 38 | 0.81 | 0.78
Modular Systems | 35 | 38 | 22 | 0.92 | 0.87
Coastal Concrete | 28 | 30 | 14 | 0.93 | 0.9
NorthSteel | 18 | 19 | 8 | 0.95 | 0.94

## Procurement
item | expected_delivery | required_on_site | variance_days | status
Valves, critical path | 2025-09-15 | 2025-09-01 | 14 | Late
Switchgear | 2025-10-01 | 2025-09-20 | 11 | Late
Compressors | 2025-09-25 | 2025-09-10 | 15 | Late
Cable trays | 2025-08-20 | 2025-08-15 | 5 | Watch
Structural steel | 2025-08-10 | 2025-08-12 | -2 | On Track
Pipe spools | 2025-09-05 | 2025-08-28 | 8 | Late
Insulation materials | 2025-08-25 | 2025-08-22 | 3 | Watch
Instrument tubing | 2025-09-10 | 2025-09-08 | 2 | Watch

## Source_Systems
system | last_refresh | refresh_frequency | staleness_flag | owner
Primavera P6 | 2025-08-28 | Weekly | Current | Planning
InEight Cost | 2025-08-25 | Weekly | Current | Cost Control
Smartsheet IFC | 2025-08-15 | Bi-weekly | Stale | Engineering
Field Progress (Excel) | 2025-08-20 | Weekly | Stale | Construction
Procurement Tracker | 2025-08-27 | Weekly | Current | Procurement

## Completeness
check | score_pct | status
Engineering Progress | 95 | Pass
Procurement Status | 88 | Fail
Physical % Progress | 97 | Pass
Cost Loading | 92 | Pass
Actual Labor Hours | 96 | Pass
Commodities And Quantities | 91 | Pass
Subcontractor Schedules | 75 | Fail
Third-Party Milestone Dates | 83 | Fail
Schedule Health Points (DCMA14) And Data Date | 98 | Pass
Critical Paths Logic Accuracy | 94 | Pass
Evaluated Remaining Durations And Forecast Dates | 85 | Fail
Reviewed With PMs And CM Prior To Finalization | 100 | Pass

## Dim_Area
area_code | area_name
A1 | A1-Tank Farm
A2 | A2-Process
A3 | A3-Marine
A4 | A4-Utilities
A5 | A5-Modular
A6 | A6-OSBL

## Dim_Discipline
discipline_code | discipline_name
CIV | Civil
CON | Concrete
STR | Structural
MEC | Mechanical
PIP | Piping
EI | E&I

## EVM_Quadrant
period | area | cpi | spi
Mar | A1 | 0.98 | 0.97
Mar | A2 | 0.96 | 0.95
Mar | A3 | 0.94 | 0.88
Mar | A4 | 0.99 | 0.96
Mar | A5 | 0.91 | 0.89
Mar | A6 | 0.95 | 0.92
Apr | A1 | 0.97 | 0.96
Apr | A2 | 0.95 | 0.94
Apr | A3 | 0.93 | 0.86
Apr | A4 | 0.98 | 0.94
Apr | A5 | 0.9 | 0.87
Apr | A6 | 0.93 | 0.91
May | A1 | 0.96 | 0.94
May | A2 | 0.94 | 0.93
May | A3 | 0.92 | 0.84
May | A4 | 0.97 | 0.93
May | A5 | 0.89 | 0.85
May | A6 | 0.92 | 0.9
Jun | A1 | 0.95 | 0.93
Jun | A2 | 0.93 | 0.92
Jun | A3 | 0.91 | 0.82
Jun | A4 | 0.96 | 0.91
Jun | A5 | 0.88 | 0.83
Jun | A6 | 0.91 | 0.89
Jul | A1 | 0.97 | 0.91
Jul | A2 | 0.92 | 0.93
Jul | A3 | 0.89 | 0.8
Jul | A4 | 0.95 | 0.9
Jul | A5 | 0.87 | 0.86
Jul | A6 | 0.92 | 0.91
Aug | A1 | 0.98 | 0.78
Aug | A2 | 0.93 | 0.93
Aug | A3 | 0.88 | 0.79
Aug | A4 | 0.96 | 0.88
Aug | A5 | 0.89 | 0.85
Aug | A6 | 0.93 | 0.9

## Critical_Milestones
milestone | baseline_date | forecast_date | drift_days | confidence | root_cause | recovery_action | trend_values | cost_impact_m
Structural Steel Complete | 2026-03-14 | 2026-04-01 | 18 | High | Minor sequencing | Weekend shifts | 6,8,10,14,16,18 | 3.2
Piping Hydrotest | 2026-07-09 | 2026-08-20 | 42 | Low | Piping labour shortage | Add 2nd crew | 8,14,22,30,36,42 | 12.5
Mechanical Completion | 2026-09-29 | 2026-11-02 | 34 | Low | Piping + vendor delays | Recovery plan under review | 5,10,16,22,28,34 | 8.8
Pre-Commissioning | 2026-12-14 | 2027-01-11 | 28 | Medium | MC delay cascade | Parallel commissioning | 4,8,12,18,22,28 | 6.4

## Risk_Triggers
trigger | rule | status
Float loss | >5d / period | Active
Rate gap | >20% | Active
IFC lag | >14d | Watch
PF drift | >1.15 / period | Active
CPI decline | 3 consecutive drops | Active

## Delay_Breakdown
view | item | delay_days | driver
Area | A5-Modular | 15 | Labour
Area | A6-OSBL | 8 | IFC
Area | A3-Marine | 6 | Vendor
Area | A2-Process | 3 | IFC
Area | A4-Utilities | 2 | Labour
Area | A1-Tank Farm | -2 | —
Discipline | Piping | 14 | Labour
Discipline | E&I | 11 | Vendor
Discipline | Mechanical | 5 | Labour
Discipline | Structural | 3 | —
Discipline | Concrete | 1 | —
Discipline | Civil | -2 | —

## Decision_Log
decision | owner | expected_impact | actual_impact | status
Add crew | Construction | -8d | -5d | Open
Release IFC | Engineering | -5d | -5d | Closed
Expedite valves | Procurement | -3d | 0d | Missed

## Why_Rate_Failing
discipline | root_cause | impact_pct | owner
Piping | Labour shortage — 2nd crew not mobilized | -35 | Construction
E&I | Cable tray rework from design change | -9 | Engineering
Mechanical | Vendor late delivery — compressors | -8 | Procurement

## Manpower
period | planned | actual | forecast
Mar | 820 | 790
Apr | 940 | 880
May | 1100 | 1020
Jun | 1280 | 1140
Jul | 1400 | 1180
Aug | 1500 | 1210
Sep | 1580 |  | 1300
Oct | 1620 |  | 1380

## Hidden_Delay
area | discipline | commodity | schedule_status | cost_status | remaining_qty | remaining_unit | actual_rate | rate_unit | days_needed | days_left | hidden_delay_days | exposure_m
A2-Process | Concrete | Foundations | Green | Green | 18000 | m³ | 600 | m³/day | 30 | 18 | 12 | 5

## Recovery_Validation
contractor | claimed_rate | rate_unit | peak_actual_rate | peak_window | shortfall_pct | duration_days | premium_k | executable
Pacific Marine | 150 | units/day | 93 | 8-week | 38 | 20 | 600 | FALSE

## PPC_Trend
period | ppc | target
Apr | 88 | 80
May | 82 | 80
Jun | 75 | 80
Jul | 68 | 80
Aug | 62 | 80

## Baseline_History
version | date | mc_date | driver | days_added | cumulative
Original | 2024-06-15 | 2027-01-15 | Contract Award | 0 | 0
Rev 1 | 2025-01-20 | 2027-03-31 | Marine scope growth (+12% piping) | 75 | 75
Forecast | 2025-08-31 | 2027-05-04 | Piping productivity shortfall | 34 | 109